Sprint 2 week 1 retrospective:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task | Start Date | Estimated End Date | End Date | Team member | Time estimated | Time invested |
| Initial meeting, adjust planification | April 1st | April 1st | April 1st | All members | 1.5h | 1.5h |
| Local settings | April 2nd. | April 2nd. | April 2nd | Daniel C. | 1h | 0.5h |
| User sign in | April 2nd | April 2nd | April 2nd | Juan R. | 2h | 2h |
| Remove expired capsules | April 2nd | April 2nd | April 2nd | Pablo R. | 1.5h | 1.5h |
| Social Network Integration: Twitter | April 2nd | April 4th | April 6th | Rafael F. | 4h | 4h |
| Update modular capsules forms | April 2nd | April 3th | April 3th | Adrián C. | 5h | 6h |
| Fix pagination and search compatibility issues | April 3th | April 3th | April 3th | Juan R. | 1.5h | 1.5h |
| Notify via email when a deadman timer is about to expire | April 3th | April 4th | April 4th | Pablo R | 1.5h | 2h |
| Front end:User sign in | April 3th | April 4th | April 4th | Daniel C | 0.5h | 0.25h |
| Basic admin. Ban and unban users | April 4th | April 6th | April 4th | Juan R. | 2h | 1.5h |
| Front end: My account page | April 4th | April 6th | April 6th | Daniel C | 1.5h | 1.25h |
| Look for improvements in automations | April 4th | April 7th | April 7th | Pablo R | 4h | 4.5h |
| Implement basic payment method | April 5th | April 7th | April 2th | Adrián C. | 4h | 4h |
| PowerPoint | April 5th | April 7th | April 7th | Rafael F | 3h | 3h |
| Front end: List and search users | April 6th | April 7th | April 7th | Daniel C | 2h | 2h |
| Rehearsal | April 7th | April 7th | April 7th | Pablo R | 1.5h | 1h |

Performance ratio:

Adrian: 0.94

Daniel: 1.44

Rafael: 1

Pablo: 1.02

Juan: 1.08

Extra tasks that appeared during the week

|  |  |  |
| --- | --- | --- |
| Task | Team member | Time invested |
| Problem with test in Travis | Daniel C | 1.5h |
| Check deadman switch when editing capsules | Daniel C. | 0.25h |
| Fix ajax search | Juan R. | 0.5h |
| Add tooltip explaining what the notification email is for | Daniel C | 1h |
| Improve sign up forms | Juan R. | 2h |