

SPRINT 2 DOCUMENTATION

Group 15

Email: [capsulefy.communications@gmail.com](mailto:capsulefy.communications@gmail.com)

Website: <https://capsulefy03.herokuapp.com>

GitHub: <https://github.com/pabreblob/capsulefy/releases> (Release 3)

Cantón Fernández, Adrián

Carpio Camacho, Daniel

Fresno Aranda, Rafael

Rebollo Lobo, Pablo

Rodríguez Regidor, Juan

Index

[Introduction 2](#_Toc5894628)

[Business Idea 2](#_Toc5894629)

[Development team 2](#_Toc5894630)

[Competitors analysis 3](#_Toc5894631)

[Cost estimation 4](#_Toc5894632)

[Development planning 5](#_Toc5894633)

[Team members performance measurement 5](#_Toc5894634)

[Improvement actions taken from the first sprint 6](#_Toc5894635)

[Sprint 2 initial planning 7](#_Toc5894636)

[Week 1 (April 1st-April 7th) 7](#_Toc5894637)

[Week 2 (April 8th-April 12th) 8](#_Toc5894638)

[Sprint 2 status after Week 1 (April 7th ) 8](#_Toc5894639)

[Problems during the first week 10](#_Toc5894640)

[Feedback received from our pilot users 11](#_Toc5894641)

[Sprint 2 Week 2 reschedule 11](#_Toc5894642)

[Sprint 2 status after Week 2 (April 12th) 12](#_Toc5894643)

[Lessons learnt 15](#_Toc5894644)

[Items produced as a result of this sprint 15](#_Toc5894645)

[Sprint 3 initial planning 16](#_Toc5894646)

[Week 1 (April 22nd-April 28th) 16](#_Toc5894647)

[Week 2 (April 29th-May 3rd) 17](#_Toc5894648)

[Piloting plan 17](#_Toc5894649)

[Test case suite 17](#_Toc5894650)

[Not logged user 17](#_Toc5894651)

[User sign up 18](#_Toc5894652)

[Premium capsules 18](#_Toc5894653)

[Important dates for our piloting plan in the future. 18](#_Toc5894654)

[User form 18](#_Toc5894655)

[User manual 18](#_Toc5894656)

[Credentials 18](#_Toc5894657)

# Introduction

The aim of this document is to provide information about the planification for this second sprint, the tasks that have been carried out and their results, as well as the conclusions the development team has arrived to after these two weeks. A quick overview of the business idea, team roles and costs is also provided, but for more extensive information about this topic please refer to the “Devising a project” document.

# Business Idea

Capsulefy is an online time capsule that allows users to store their memories and share them in the future. Users will be able to create a time capsule, attach a message to it, load files such as videos or images into it and set a date when they want the capsule to be released.

The capsules can also be connected to the user’s social networks so that a message is automatically posted when the capsule is published. Users will also be able to select a list of emails that will receive a notification message.

One of the main selling points of our product is allowing people to leave a message behind in case they pass away. For this reason, we will offer a dead-man switch option that once activated, will automatically release the capsule regardless of its publication date if the user hasn’t refreshed the counter after a certain period of time.

Our capsules also offer extra features such as the possibility of splitting them into different modules, each of them with a different release date, or making them private so that they won’t appear when listing the capsules.

We will be offering two different types of capsules: Free and premium capsules.

Each registered user will be able to create free capsules and upload files to them up to a maximum of 20mb in total. These capsules can be scheduled up to one year in the future and will be deleted 6 months after their release. These capsules can’t be made private, split into modules or have a dead-man switch set up

Premium and modular capsules will cost 11.99 € each, can store up to 500mb of files and will not have a limit on how far into the future they can be scheduled, nor will they disappear after being released.

# Development team

Our team is composed by five members, each one with different roles and responsibilities:

* Pablo Rebollo Lobo. His roles are project manager and backend developer. His main technological competencies are Spring, Django and PHP.
* Adrián Cantón Fernández, whose roles are business manager and full-stack developer. His main technological competencies are Django, Java and Bootstrap.
* Daniel Carpio Camacho, analyst and frontend developer. His main technological competencies are Django, JavaScript and Bootstrap.
* Juan Rodríguez Regidor, whose roles are requirements engineer and backend developer. His competencies are Django, Python and Bootstrap.
* Rafael Fresno Aranda. His role is backend developer and will also be in charge of the interaction of our product with other applications. His main technological competencies are Node.js, Django and PHP.

Our commitment as a team is to develop our business idea in order to create a minimum viable product in a good enough state so that it can receive appropriate feedback to decide whether or not release the full version to the market and apply that feedback to improve our product.

To reach this goal, we are compromised to meet the deadlines, listen to the feedback and cooperate within the team so that we can provide a product that meets our quality standards.

# Competitors analysis

We did a market research in order to determine which existing online services our product will be competing with, which are their main features and what makes our product different from them. We found 4 other similar services. The results of comparing them to our product are the following:



Figure 1: Competitors analysis table

We reached the conclusion that we are treading into an already existing market, but an undeveloped one, where we can offer features that makes us distinct from our competitors, such as the interaction with social networks and the publication of content in case the user has not logged in for a very long time.

There are other indirect competitors, such as official last wills or more traditional methods of sharing memories like photo albums, but they won’t be able to offer the possibility of quickly sharing their contents online.

The innovation of our app are these two features no other application similar to us provides: The dead man switch and social network interaction. While the development of these features does not imply that we are innovating from a technological viewpoint, since we will be using already existing technologies (OAuth, API calls…), the way we are incorporating them into our business model is something new that has not been tried by our more direct competitors. Thanks to these features, our service is highly customizable so that every user can tailor their time capsules to their needs.

# Cost estimation

Because we will be using Google Firebase to store all the files our users will upload to our system, we need to take into account the individual cost per user. By using Amazon S3, we will be charged 0.026 USD per GB per month.

Assuming we will be offering 500mb of storage in each of our Premium/Modular capsules, the cost of maintaining each 500mb capsule yearly is 0.156 USD (0.14€).

Assuming free users have 20 mb of storage, the yearly cost of maintaining a free user will be of 0.00624 USD (0.0127€).

In order to decide our storage and hosting funds, we will consider the cost of maintaining 2,000 premium capsules and 20,000 free users for a year, as well as an estimation of the cost of hosting our website and our database.

Our team has come up with 4 different cost estimations: A pessimistic one, an optimistic one, and two realistic estimations. These estimations cover costs during the development of our product, whose duration will be of 4 months, and some funds which may be used in order to deal with the risks that appear during the development or to cover initial server and advertisement costs. The factors that will affect our budget are the following:

* Team members’ salaries.
* Hardware amortization.
* Advertising funds for the first 6 months.
* Storage and hosting funds for the first year.
* Risk prevention funds.
* Taxes.

Because we will be using Google Firebase to store all the files our users will upload to our system, we need to take into account the individual cost per user. By using Amazon S3, we will be charged 0.026 USD per GB per month.

Assuming we will be offering 500mb of storage in each of our Premium/Modular capsules, the cost of maintaining each 500mb capsule yearly is 0.156 USD (0.14€).

Assuming free users have 20 mb of storage, the yearly cost of maintaining a free user will be of 0.00624 USD (0.0127€).

In order to decide our storage and hosting funds, we will consider the cost of maintaining 2,000 premium capsules and 20,000 free users for a year, as well as an estimation of the cost of hosting our website and our database.

As for advertising funds, firstly we have to determine a target audience. Our product is targeted to people who regularly uses internet and social media. The age segments targeted are young people and middle-age people.

Our goal is to advertise ourselves on the internet. For that reason, we will be using google ads. Because we offer integration with Facebook and Twitter, reaching out to the users of these platforms is also considered a key aspect of our marketing strategy.

Google ads charge business for each time their advertising is clicked. Each business can set how much they can be charged, and depending the price set, their ad will be more visible.

Because we are a small company, we will be setting the cheapest price possible within the range of prices our possible competitors for that ad spot pay, which is one of around 220€ per month, with an estimated performance of 137‑229 clicks per month

Facebook also allows us to customize how much would be willing to spend on a weekly basis. We have decided to spend about 140€ monthly for a Facebook advertisement which targets people of between 18 and 50 years old.

Same as Facebook, Twitter allows us to set a daily price. We will be using a similar budget to the one for Facebook, 5€ daily, which means ~150€ monthly for an audience between 18 and 49 years old.

In conclusion, we will be spending approximately 510€ monthly in advertisement. If in our project costs we are going to include the cost for the first 6 months, we will have a total cost of 3060€.

After these first 6 months, we will evaluate how this approach is performing, and depending on that we will decide whether increase or decrease our budget.

Overall, we expect this project to have a cost of 30K euros approximately.

# Development planning

We will develop our product following the SCRUM methodology. The development of our prototype will be split into three sprints. The results generated from each sprint will be the following:

* Sprint 1: Prototype with working core use cases and a piloting plan in order to start gathering feedback.
* Sprint 2. Full working MVP. This means that not only the core use cases will be implemented, but also the payment module, the registration module and the basic admin will be working. The core use cases may be to need adapted according to the feedback resulting from the previous sprint.
* Sprint 3: Polished MVP which will take into account all the feedback from previous sprints.

# Team members performance measurement

In order to measure our productivity, we will be using Toggl. At the beginning of each sprint, we will have the tasks with their corresponding time estimation. At the end of the week, the estimated time will be divided by the real time invested in that task. This will be the efficacy ratio of this task. For each team member, the mean of their efficiency will be calculated, and it will be the member’s performance ratio. If the task is left unfinished, their ratio will be used in order to calculate a member effectivity if its <1, because a unfinished task should only affect negatively to the efficiency ratio of a person and not the other way around. A ratio between 0.8 and 1.2 is considered the expected performance.

A ratio between 1.2 and 1.5 is considered as more efficient than expected, and a ratio bigger than 1.5 is considered more efficient than desired and the causes for this will be investigated.

A ratio between 0.8 and 0.5 is considered less efficient than expected, and a ratio smaller than 0.5 means that there have been major issues with that task and the reason why will be investigated.

Besides this ratio, it will also be taken into account whether or not a user has finished his tasks, and in case there are some tasks left unfinished, we will try to find out the reason and act accordingly.

In order to measure the project manager’s efficiency, we will factor in his performance in his assigned tasks and the overall performance of the team, as one of the project manager’s responsibilities is to ensure that the team is working well. The formula that we will be using is the following:

**PM tasks performance \* average team performance – Total days of delays in the tasks\*0.1**

Reasons why the performance may be better than expected:

* The tasks assigned to a member where easier than expected and therefore, took less time than the estimated. It will be taken into account so that he may receive a bigger workload in the future and the member will be suggested to review in depth the work he has carried out if he finishes it in less time than expected.
* Bad time estimation for that task. For the next set of similar tasks, their estimated time will be reduced until it is similar to the one that carrying out that task took.

If the performance is worse than expected, it is a bigger problem than taking less time than expected. The reasons why this may have happened are the following:

* Bad time estimation, just as when it takes less than it should. The same protocol previously mentioned applies to this case.
* A team member is not working properly. The member will be told that his attitude must change and will be closely monitored for the next set of tasks.
* Unexpected problems or the member did not have the skill required to complete the task in that timeframe. If there where unexpected obstacles, these problems and how they were solved will be written down in order to easily deal with them should the appear again. If the problem was that the team member was simply not able to do the tasks within the estimated time, it will be taken into account so that he is not assigned similar tasks and these are assigned to more efficient members.

An acceptable ratio is one whose value is between 0.5 and 1.5, if the performance of a member is not contained in that interval, we will know there is a problem that must be urgently dealt with. Regardless, the strategies available Will always be applied so that all the team can reach an optimal efficiency ratio, just with less urgency the closer their ratio is to the ideal.

# Improvement actions taken from the first sprint

Firstly, when planning, we will divide our workload into smaller tasks with shorter duration. In order to measure if this is helping us improve, we will look at 3 things:

* Performance ratio.
* Maximum delay in days out of all the tasks. Maximum delay acceptable: 2 days.
* How many hours did each task take. Maximum hours per task: 6 hours.
* How many days did each task take. Maximum days per task: 6 days

If any of these thresholds is reached, that means we did a bad time estimation and should have probably divide these tasks into smaller ones.

More documentation of bugs and issues:

Each bug or problem found should be documented in our repository wiki.

# Sprint 2 initial planning

## Week 1 (April 1st-April 7th)

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Task | Start Date | Estimated End Date | Team member | Time estimated |
| Initial meeting, adjust planification | April 1st | April 1st | All members | 1.5h |
| Local settings | April 2nd. | April 2nd. | Daniel C. | 1h |
| User sign up | April 2nd | April 2nd | Juan R. | 2h |
| Remove expired capsules | April 2nd | April 2nd | Pablo R. | 1.5h |
| Social Network Integration: Twitter | April 2nd | April 4th | Rafael F. | 4h |
| Update modular capsules forms | April 2nd | April 3rd | Adrián C. | 5h |
| Fix pagination and search compatibility issues | April 3rd | April 3rd | Juan R. | 1.5h |
| Notify via email when a deadman timer is about to expire | April 3rd | April 4th | Pablo R | 1.5h |
| Front end:User sign up | April 3rd | April 4th | Daniel C | 0.5h |
| Basic admin. Ban and unban users | April 4th | April 6th | Juan R. | 2h |
| Front end: My account page | April 4th | April 6th | Daniel C | 1.5h |
| Look for improvements in automations | April 4th | April 7th | Pablo R | 4h |
| Implement basic payment method | April 5th | April 7th | Adrián C. | 4h |
| PowerPoint | April 5th | April 7th | Rafael F | 3h |
| Front end: List and search users | April 6th | April 7th | Daniel C | 2h |
| Rehearsal | April 7th | April 7th | Pablo R | 1.5h |

## Week 2 (April 8th-April 12th)

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Task | Start Date | End Date | Team member | Time estimated |
| Meeting to discuss class and pilot user feedback | April 8th | April 8th | All members | 1.5h |
| User interface | April 9th | April 11th. | Daniel C. | 7h |
| Social Network Integration: Facebook | April 9th | April 11th | Rafael F. | 4h |
| Make Premium capsules payment-only but giving us a way to test them | April 9th | April 10th | Adrián C. | 4h |
| Basic admin: Dashboard with application data | April 9th | April 10th | Juan R. | 3h |
| Apache jmeter tests | April 9th | April 11th | Pablo R | 4h |
| SonarCloud tests | April 11th | April 12th | Adrián C | 2h |
| Allow user to edit their notification mail | April 11th | April 11th | Juan R | 2h |
| Sprint review and Sprint 3 planification meeting | April 11th | April 11th | All members | 1.5h |
| PowerPoint | April 11th | April 12th | Rafael F. | 3h |
| Deliverable documentation | April 11th | April 12th | Pablo R | 4h |

# Sprint 2 status after Week 1 (April 7th )

The tasks planned were carried out successfully. Only one task suffered a delay due to the person in charge of it had exams we did not take into account when planning for this week. The task suffered a delay of 2 days, but it was successfully completed The status of the tasks at the end of this first week were the following (meetings will be excluded from this analysis, as they all took place within the time estimated):

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task | Start Date | Estimated End Date | End Date | Team member | Time estimated | Time invested |
| Initial meeting, adjust planification | April 1st | April 1st | April 1st | All members | 1.5h | 1.5h |
| Local settings | April 2nd. | April 2nd. | April 2nd | Daniel C. | 1h | 0.5h |
| User sign in | April 2nd | April 2nd | April 2nd | Juan R. | 2h | 2h |
| Remove expired capsules | April 2nd | April 2nd | April 2nd | Pablo R. | 1.5h | 1.5h |
| Social Network Integration: Twitter | April 2nd | April 4th | April 6th | Rafael F. | 4h | 4h |
| Update modular capsules forms | April 2nd | April 3rd | April 3rd | Adrián C. | 5h | 6h |
| Fix pagination and search compatibility issues | April 3rd | April 3rd | April 3rd | Juan R. | 1.5h | 1.5h |
| Notify via email when a deadman timer is about to expire | April 3rd | April 4th | April 4th | Pablo R | 1.5h | 2h |
| Front end:User sign in | April 3rd | April 4th | April 4th | Daniel C | 0.5h | 0.25h |
| Basic admin. Ban and unban users | April 4th | April 6th | April 4th | Juan R. | 2h | 1.5h |
| Front end: My account page | April 4th | April 6th | April 6th | Daniel C | 1.5h | 1.25h |
| Look for improvements in automations | April 4th | April 7th | April 7th | Pablo R | 4h | 4.5h |
| Implement basic payment method | April 5th | April 7th | April 2th | Adrián C. | 4h | 4h |
| PowerPoint | April 5th | April 7th | April 7th | Rafael F | 3h | 3h |
| Front end: List and search users | April 6th | April 7th | April 7th | Daniel C | 2h | 2h |
| Rehearsal | April 7th | April 7th | April 7th | Pablo R | 1.5h | 1h |

Besides the planned tasks, new tasks appeared through the week:

|  |  |  |
| --- | --- | --- |
| Task | Team member | Time invested |
| Problem with test in Travis | Daniel C | 1.5h |
| Check deadman switch when editing capsules | Daniel C. | 0.25h |
| Fix ajax search | Juan R. | 0.5h |
| Add tooltip explaining what the notification email is for | Daniel C | 1h |
| Improve sign up forms | Juan R. | 2h |

The performance ratios of our team members at the end of the week were the following:

* Adrián Cantón: 0.94
* Daniel Carpio: 1.44
* Rafael Fresno: 1
* Pablo Rebollo (Project manager): 0.93
* Juan Rodríguez: 1.08

After reviewing these ratios, we came to the conclusion that our performance had improved significantly, and now all the members were in the ideal performance range except one who performed better than expected. Looking at this, we can say that the actions we took helped us to achieve a better performance. Taking a look at the other metrics we previously defined in order to measure how good the actions we took from what we learned on the previous sprint were:

* Maximum delay in days out of all the tasks: Only one task was delayed, and it had a 2 days delay, which was the limit we decided for this metric.
* How many hours did each task take. The maximum number of hours a task took was 6 hours.
* How many days did each task take. The maximum amount of days a task took was 5 days.

With these results, we can say that our actions helped us improve, but there is still room for improvement. As for our GitHub wiki, last sprint it only had one entry. As of today, there are 5 entries, explaining how to fix some troubles we have run into.

The accumulated costs of this development sprint and all the previous weeks of work are the following:

# Problems during the first week

We faced three problems during this week:

* On April 1st, Django was updated to version 2.2. In this version, “None” cannot be passed as a value to encode. We did this in some of our tests, but because we were not using the 2.2 version, we did not notice any problem. However, when executing our tests in Travis, they were launched using the 2.2 version, and therefore, failed. We had to investigate the reason of this failure and fix it. As a solution, we could either force Travis to use an older Django version or upgrade the one we were using. We decided to upgrade the Django version we were using, because it probably works better and will receive more support. However, this means that we need to look out for other errors that may appear due to the version change and pay attention in case another update rolls out.
* On April 7th, we decided to deploy our application in order to test in and record the demo videos to shown on class the next day. However, we noticed that a lot of server errors that did not happen while deploying in localhost. We spent a few hours just to realize that the problem was caused by migration conflicts. We managed to fix these problems, but we had to spend a lot of time and as a result, the quality of our demo videos was not as good as desired. In order to solve any unexpected issues when deploying, we have decided to set our deployment date 2 days before the deadline, this means we deploy our application on Wednesday, so we have 2 days to test the application in our server. Because of this, we will need to adjust our week 2 planning.
* We waited for our weekly meeting on Monday in the afternoon to talk about the feedback provided by our pilot users and what actions are we going to take about it. Because of this, we were not able to listen our evaluator’s opinions about this during our class. To prevent this, we will have a meeting on Saturdays when we receive the opinion of our pilot users, even if short. This way, we can start thinking about possible actions to take and show them during class.

# Feedback received from our pilot users

On April 6th, we retrieved the forms we handed to our pilot users. Our seven pilot users answered it, and the result we obtained were the following:

* All of them were able to list and display capsules, create, edit or delete free capsules and create, edit or delete premium capsules
* One person was not able to delete a module, and say it was confusing

As for comments and feedback they provided, we have highlighted the following opinions:

* There was a lack of confirmation button when deleting capsules. **Action that we will take**: Implement confirmation buttons when deleting a capsule or a user’s data
* Lack of date pickers when having to input a date. They found tedious writing a date manually. This feedback was provided not only by one user, most of them hold the same opinion. **Action that we will take**: Add date pickers in our date input fields.
* No return button when displaying a capsule. **Action that we will take**: Add “return” button when displaying capsules or a user’s profile.
* Some of the features were not very clear to them, such as the dead-man switch. **Action that we will take:** Add a “help” section with a video explaining how does our deadman switch work.
* When trying to access to a page that did not exist, they found the 404 page not friendly to the user. **Action that we will take:** Work on a 404 page that looks better and that gives the user the option to return to our main page.
* When adding multiple emails to the notification email in a capsule, there should be a text, a tooltip or a placeholder showing that in order to add more than one email, these must be separated by a comma. **Action that we will take:** Add a placeholder showing how to input multiple emails.

Overall, they found our application interesting, but they also said that there is a lot of room for improvement on the UX department.

# Sprint 2 Week 2 reschedule

Due to the problems we had encountered during the first week and the fact that we had already received feedback from our pilot users to work with, we decided to reschedule our second week of this sprint. The tasks that were decided to be carried out are the following:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task | Start date | | Estimated end date | Team member | Estimated time |
| Meeting to discuss class and pilot user feedback | | April 8th | April 8th | All members | 1.5h |
| Fix functional tests | | April 8th | April 10th. | Adrián C. | 0.75h |
| Admin dashboard | | April 8th | April 10th | Juan R. | 3h |
| Delete user’s data | | April 8th | April 10th | Pablo R. | 1.5h |
| Add datepicker | | April 8th | April 10th | Adrián C. | 1h |
| Fix listing of notification mails in “my account” | | April 8th | April 10th | Daniel C | 0.5h |
| Add confirm button when deleting users or capsules | | April 8th | April 10th | Daniel C | 1h |
| Allow user to edit their notification mail | | April 8th | April 10th | Rafael F | 1h |
| Add “about us” page | | April 8th | April 10th | Daniel C | 0.25h |
| Add return button when displaying a capsule or user | | April 8th | April 10th | Daniel C | 1h |
| Correct previous front end errors and improvements based on feedback | | April 8th | April 10th | Daniel C | 1.5h |
| Deploy application | | April 10th | April 10th | Adrián C | 2h |
| Test the deployed application | | April 10th | April 12th | Daniel C  Juan R | 2h each |
| PowerPoint | | April 10th | April 12th | Rafael F | 5h |
| Pilot user form | | April 8th | April 12th | Pablo R | 1.5h |
| User manual | | April 8th | April 12th | Pablo R | 1h |
| Sprint 2 retrospective documentation | | April 8th | April 12th | Pablo R | 4h |
| Rehearsal | | April 20th | April 21th | Pablo R | 1.5h |

# Sprint 2 status after Week 2 (April 12th)

The tasks planned were carried out successfully. There were no delays and managed to deploy our application the day it was planned to. The rehearsal task, although belonging to this sprint, is not taken into account, as it will happen when the presentation date draws closer.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task | Start date | Estimated end date | End date | Team member | Estimated time | Time invested |
| Meeting to discuss class and pilot user feedback | April 8th | April 8th | April 8th | All members | 1.5h | 1.5 |
| Fix functional tests | April 8th | April 10th. | April 8th | Adrián C. | 0.75h | 0.5 |
| Admin dashboard | April 8th | April 10th | April 9th | Juan R. | 3h | 3h |
| Delete user’s data | April 8th | April 10th | April 8th | Pablo R. | 1.5h | 2h |
| Add datepicker | April 8th | April 10th | April 9th | Adrián C. | 1h | 1h |
| Fix listing of notification mails in “my account” | April 8th | April 10th | April 10th | Daniel C | 0.5h | 0.2h |
| Add confirm button when deleting users or capsules | April 8th | April 10th | April 10th | Daniel C | 1h | 0.4h |
| Allow user to edit their notification mail | April 8th | April 10th | April 10th | Rafael F | 1h | 1h |
| Add “about us” page | April 8th | April 10th | April 9th | Daniel C | 0.25h | 0.25h |
| Add return button when displaying a capsule or user | April 8th | April 10th | April 10th | Daniel C | 1h | 0.25 |
| Correct previous front end errors and improvements based on feedback | April 8th | April 10th | April 10th | Daniel C | 1.5h | 1.5h |
| Deploy application | April 10th | April 10th | April 10th | Adrián C | 2h | 1.5h |
| Test the deployed application | April 10th | April 12th | April 12th | Daniel C  Juan R | 2h each | 2h each |
| PowerPoint | April 10th | April 12th | April 12th | Rafael F | 5h | 5.5h |
| Pilot user form | April 8th | April 12th | April 11th | Pablo R | 1.5h | 2h |
| User manual | April 8th | April 12th | April 11th | Pablo R | 1h | 0.75h |
| Sprint 2 retrospective documentation | April 8th | April 12th | April 12th | Pablo R | 4h | 4h |
| Rehearsal | April 20th | April 21th |  | Pablo R | 1.5h | - |

Besides these tasks, other unplanned tasks appeared:

|  |  |  |
| --- | --- | --- |
| Task | Team member | Time invested |
| Update populate | Pablo R | 0.5h |
| Fix edit capsules url | Adrián C | 0.25h |

After these two weeks of development, the accumulated cost of our project is the following:

|  |  |
| --- | --- |
| Project duration | 9 weeks |
| Total spent in salaries | 9217 € |
| Equipment | 238€ |
| Hosting | 0€ |
| Advertising | 0€ |
| Risk prevention fund | 2724€ |
| Total costs | 12179€ |
| Percentage of project completion | 43% |
| Percentage of budget spent | 39% |

Our development cost is still within the estimated margin. In our next sprint, the hosting and advertising costs will be factored in, as it is the last development sprint planned.

The performance ratios of our team members at the end of the week were the following:

* Adrián Cantón: 1.33
* Daniel Carpio: 1.9
* Rafael Fresno: 0.96
* Pablo Rebollo (Project manager): 1.23
* Juan Rodríguez: 1

After reviewing these ratios, we came to the conclusion that our performance is getting better, to the point where our ratios are above what is considered optimal. There are multiple reasons for this ratios to be higher than expected:

* Because we needed to deploy earlier than initially planned at the beginning of the sprint, some more complex tasks were left out, and most of the work this week was focused on improving already existing features and fix bugs. Because we focused on simpler tasks, the performance was very high
* We faced little to no technical problems this week. This is also related to the fact that our tasks were not very complex.
* The front end tasks during the first sprint took a lot of time. However, because our front end key elements were already laid out this sprint, all the front end tasks were done much more quickly than expected.

Taking a look at our other metrics, we see that our performance this sprint has been very positive overall:

* Maximum delay in days out of all the tasks: No tasks were delayed.
* How many hours did each task take. The maximum number of hours a task took was 5.5 hours.
* How many days did each task take. The maximum amount of days a task took was 2 days.

We can see that our previous measures have been effective and that our performance this sprint has improved greatly. However, we will continue to monitor these metrics in order to detect any possible problems. Now that we have reached the point where we are performing better than expected, we will try to make some changes in order to capitalize on that extra efficiency. These changes will be talked about in the next section.

# Lessons learnt

* Updates in the software we are using can cause us problems. In order to fix that, we need to monitor the software we are using and whenever a new update pops up, test that there are no compatibility problems and update our software if necessary.
* It is very important to deploy our application and leave enough time to test it and react if there are some problems. As we have done during our second week, we will always deploy our application at least 2 days before the deadline.
* In order to benefit from feedback about our piloting plan from our evaluators, we need to decide what actions are we going to take once we have user’s feedback before Monday’s class. We have decided to hold a meeting on Saturdays once we received our user’s feedback.
* Pay attention to changes in our application and how does it affect to the data we have previously populated our database with so that there are no conflicts. In order to solve this, there will be a dedicated task of reviewing our populate script before deployment.
* Because the performance in this sprint has been higher, we will start lowering the estimated time of our tasks and add more tasks to our first week of the 3rd sprint. To monitor these changes, we will use the same metrics as this sprint: Performance ratio, days of delay, maximum number of hours a task takes and maximum amount of days a task takes.
* To know better how many bugs are appearing during our development and the amount of time that is being invested in solving them, we will look at the ratio of GitHub issues tagged as “bug” divided by the number of normal issues. We will also look at the ratio of hours invested in bugfixing and hours invested in developing the app.

# Items produced as a result of this sprint

Full working MVP of our application, deployed on <https://capsulefy03.herokuapp.com>

Demo videos of our application, which can be found in our slides. The release of this sprint in GitHub can be found on <https://github.com/pabreblob/capsulefy/releases> (Release 3).

Updated user manual and pilot user form.

All the documentation related to our Sprint 2, what had we planned, how it progressed and the sprint retrospective.

# Sprint 3 initial planning

Because at this point our MVP is already fully working, it is not possible at this point in time to make a more specific planification for this sprint, as a big part of the tasks that will be assigned are related to the feedback we will receive from pilot users and improvements our team can think of.

## Week 1 (April 22nd-April 28th)

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Task | Start Date | Estimated End Date | Team member | Time estimated |
| Initial meeting, review user’s feedback | April 22nd | April 22nd | All members | 1.5h |
| Clean up the code | April 22nd | April 23rd | Juan R. | 3h |
| Improve checkboxes | April 22nd. | April 22nd. | Daniel C. | 1h |
| Improve responsive design | April 23nd | April 26th | Daniel C. | 5h |
| Facebook integration | April 22nd | April 25th | Rafael F. | 1.5h |
| Apache JMeter | April 22nd | April 25th | Pablo R. | 4h |
| SonarCloud | April 22nd | April 24th | Adrián C. | 5h |
| Fix images proportions in capsules | April 24th | April 25th | Daniel C. | 0.5h |
| Improve dashboard | April 24th | April 25th | Juan R. | 2h |
| Review populate | April 25th | April 25th | Pablo R | 1h |
| Deployment | April 26th | April 26th | Adrián C. | 1.5h |
| PowerPoint | April 26th | April 28th | Rafael F | 3h |
| Rehearsal | April 28th | April 28th | Pablo R | 1h |

## Week 2 (April 29th-May 3rd)

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Task | Start Date | End Date | Team member | Time estimated |
| Meeting to discuss class feedback | April 29th | April 29th | All members | 1.5h |
| Improve firebase application | April 29th | April 30th | Adrián C | 2h |
| Improve automation | April 29th | April 30th | Pablo R | 2h |
| Add contents of our landing site to our deployed app | April 29th | April 30th. | Daniel C. | 3h |
| Add datepicker in user sign up form | April 29th | April 30th. | Daniel C. | 0.5h |
| Fix Social Network problems | April 29th. | April 30th. | Rafael F. | 2h |
| Fix backend related problems | April 29th | April 30th | Juan R. | 2h |
| Review populate | April 30th | April 30th | Juan R. | 1h |
| Deploy application | May 1st | May 1st | Adrián C | 2h |
| Test the deployed application | May 1st | May 3rd | Daniel C  Juan R | 2h each |
| PowerPoint | May 1st | May 3rd | Rafael F | 5h |
| Pilot user form | May 1st | May 3rd | Pablo R | 1.5h |
| User manual | May 1st | May 3rd | Pablo R | 1h |
| Sprint 3 retrospective documentation | May 1st | May 3rd | Pablo R | 4h |
| Rehearsal | May 3rd | May 3d | Pablo R | 1.5h |

# Piloting plan

Our piloting plan will consist of:

* Creating a user manual with implemented core functions about our application so that pilot users may know what actions they can do in it. This manual can contain pictures or links to videos to explain its use.
* Creating a test case suite for pilot users to execute it.
* Creating an environment where users can try our application and give them credentials to log in and try it.
* Creating a form in order to know users’ opinions and get feedback to improve our product.
* Collect feedback from them, use it to improve our product and send them a new test case suit to receive new information.

## Test case suite

### Not logged user

* List and search public capsules
* Display public capsules

### User sign up

* Sign up as a new user
* Edit user notification mail and Twitter account

### Premium capsules

* Create a premium capsule
* Pay for the capsule
* Edit capsule
* Edit module
* Delete module
* Delete capsule

## Important dates for our piloting plan in the future.

|  |  |  |
| --- | --- | --- |
| Date | Description | Person in charge |
| 12/04/19 – 22/04/19 | Pilot users receive and fill new form | Adrián C |
| 22/04/19 | Receive users feedback | Adrián C. |
| 22/04/19 | Planification using feedback | All |
| 22/04/19 – 03/05/19 | Develop | All |
| 04/05/19 -12/05/19 | Pilot users receive and fill last form | Adrián C. |
| 12/05/19 | Receive users feedback | Adrián C. |
| 13/05/19 | Planification using last feedback | All |

## User form

User’s feedback will be collected through the following survey: <https://forms.gle/NmN7pxV28oh9hCcV6>

The survey has been written in Spanish, as it is the main language of all our pilot users.

## User manual

A document on this same deliverable called “User Manual.pdf” includes the information necessary to use our prototype. The aim of that document is to make easier for our pilot users and evaluators to test our application. The form that will be provided to the pilot users will contain an explanation on how answer each of the questions too. A Spanish version will be available for our users, while the English version is the one that will be included in our deliverable for consistency.

## Credentials

Our pilot users will receive credentials, but they will be told to create a new user from scratch in order to test our signup form. These credentials will only be used in case they are unable to sign up to our system.